## Activities
Activity ID | Activity description | Optimistic | Most-Likely | Pessimistic | Predecessor activity
1 | Contract date | 0 | 0 | 0
2 | Financial Close | 0 | 0 | 0
3 | Design | 819 | 920 | 1435 | 1
4 | Obtaining Commencement Certificate | 105 | 130 | 194 | 1
5 | Obtainment of Commencement Certificate | 0 | 0 | 0 | 4,2
6 | Date of commencement | 0 | 0 | 0 | 5
7 | Maintain existing road assets A9 / A1 / A6 | 976 | 1284 | 1836 | 6
8 | Conditioning, Cables and Conducts, permits | 168 | 200 | 268 | 6
9 | Preload | 324 | 395 | 525 | 6
10 | Construction of new Aqueduct | 200 | 260 | 341 | 6
11 | Construction of the Amsterdam-Rijn Canal bridge | 285 | 335 | 492 | 6
12 | Road works southern A1 lane | 113 | 128 | 189 | 9,10,11
13 | Commissioning of the southern A1 new lane | 0 | 0 | 0 | 12
14 | Producing parts of Railbridge part 1 | 223 | 251 | 366 | 6
15 | Producing parts of Railbridge part 2 | 194 | 220 | 350 | 14
16 | Assembling a railway bridge on location | 559 | 674 | 971 | 14
17 | Moving Railway Bridge in place during Train Free Period | 0 | 0 | 0 | 16
18 | Road works northern A1 lane | 109 | 130 | 191 | 17
19 | Commissioning of the Northern A1 new lane | 0 | 0 | 0 | 18
20 | Road and construction works new part junction Diemen | 477 | 530 | 848 | 13
21 | Build new viaducts A6 | 304 | 400 | 532 | 6
22 | Build second Hollandse bridge | 286 | 340 | 459 | 6
23 | Road and construction works junction Muiderberg | 716 | 930 | 1237 | 6
24 | Road works eastern part A6 | 90 | 100 | 130 | 21, 22
25 | A6 East ready | 0 | 0 | 0 | 24
26 | Reconstruction western part A6 | 324 | 400 | 532 | 25
27 | Commissioning A6 | 0 | 0 | 0 | 18,23,26
28 | Road works existing part Diemen junction | 71 | 90 | 130 | 19,20
29 | Request Availability Certificate | 0 | 0 | 0 | 28
30 | Assess and obtain Availability Certificate | 16 | 20 | 27 | 29
31 | Demolition old A1 (part 1) | 54 | 61 | 91 | 30
32 | Demolition old A1 (part 2) | 23 | 30 | 48 | 31
33 | Greenery for old A1 | 77 | 90 | 129 | 31
34 | Applications and obtaining partial completion certificates | 104 | 120 | 161 | 30
35 | Request Completion Certificate | 0 | 0 | 0 | 33
36 | Assess and obtain Certificate of Completion | 17 | 20 | 27 | 35
37 | Scheduled Completion Date | 0 | 0 | 0 | 36
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum duration of the activity. The user must define this quantity. To generate random values, you may apply this formula in the cells: =ROUND(RANDBETWEEN(130,160)/100*D7,0)
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely duration of the activity. The user must define this quantity
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum duration of the activity. The user must define this quantity. To generate random values, you may apply this formula in the cells: =ROUND(RANDBETWEEN(130,160)/100*D6,0)

## Mitigations
|  | Objective Time |  |  |  |  | Objective Cost |  |  | User traffic experience
Mitigation ID | Mitigation measure | Minimum time | Most likely time | Maximum time | Relations | dependency factor (eta) | Minimum cost | Most likely cost | Maximum cost | Minimum nuisance | Most likely nuisance | Maximum nuisance
1 | Extra engineering design office personnel | 99.45 | 101.4 | 101.4 | 3 | 0.5 | 118846.1538 | 120000 | 120000 | 0 | 0 | 0 | Additional design personnel can streamline the planning process but have minimal direct impact on traffic.
2 | Extra software design capacity | 13.65 | 13.65 | 13.65 | 4 | 0.5 | 30000 | 30000 | 30000 | 0 | 0 | 0 | Similar to engineering design personnel, this can improve efficiency behind the scenes with minimal direct impact on traffic.
3 | Extra maintenance engineers | 103.35 | 126.75 | 126.75 | 7 | 0.5 | 136153.8462 | 150000 | 150000 | 0.90769 | 1 | 1 | Maintenance engineers can help keep traffic moving smoothly by quickly addressing any issues that arise, slightly reducing potential traffic disruptions.
4 | Extra administrators for permitting | 42.9 | 50.7 | 56.55 | 8 | 0.5 | 44307.6923 | 48000 | 50769.2308 | 0 | 0 | 0 | This can expedite the permitting process, potentially reducing project delays, but has a minimal direct impact on traffic.
5 | Applying extra preloading material | 40.95 | 50.7 | 50.7 | 9 | 0.5 | 677884.6154 | 750000 | 750000 | 5.4231 | 6 | 6 | This can require additional space and time, potentially impacting traffic flow more significantly.
6 | Adding extra on site construction flow | 91.65 | 101.4 | 107.25 | 10 | 0.5 | 190384.6154 | 200000 | 205769.2308 | 9.5192 | 10 | 10 | More on-site construction flow can lead to increased disruptions and potential bottlenecks in traffic.
7 | Extra prefab construcion capacity | 117 | 126.75 | 128.7 | 11 | 0.5 | 144230.7692 | 150000 | 151153.8462 | 0.96154 | 1 | 1.0077 | Prefab construction can speed up the building process and might reduce the time roads are impacted, slightly improving traffic experience.
8 | Extra M&E engineers | 50.7 | 50.7 | 50.7 | 12 | 0.5 | 60000 | 60000 | 60000 | 3 | 3 | 3 | Can improve efficiency and reduce downtime in construction, marginally improving traffic flow.
9 | Extra welding equipment and personnel | 52.65 | 64.35 | 64.35 | 14 | 0.5 | 90909.0909 | 100000 | 100000 | 5.4545 | 6 | 6 | Additional equipment and personnel can speed up construction but might require more space, affecting traffic.
10 | Extra temporary soil measures | 44.85 | 50.7 | 52.65 | 15 | 0.5 | 235576.9231 | 250000 | 254807.6923 | 5.6538 | 6 | 6.1154 | Such measures can be necessary for safety and stability but might take up additional space, impacting traffic flow.
11 | Ancillary on standby | 200.85 | 202.8 | 222.3 | 16 | 0.5 | 199038.4615 | 200000 | 209615.3846 | 4.976 | 5 | 5.2404 | Having standby resources can reduce downtime during unexpected events, slightly improving traffic conditions.
12 | Extra M&E engineers | 13.65 | 13.65 | 13.65 | 18 | 0.5 | 30000 | 30000 | 30000 | 3 | 3 | 3 | Can improve efficiency and reduce downtime in construction, marginally improving traffic flow.
13 | Extra excavation capacity | 95.55 | 101.4 | 101.4 | 20 | 0.5 | 121394.2308 | 125000 | 125000 | 9.7115 | 10 | 10 | Increased excavation work can significantly disrupt traffic, especially if additional lanes or areas need to be closed.
14 | Extra concrete workers / carpenters | 81.9 | 101.4 | 107.25 | 21 | 0.5 | 67788.4615 | 75000 | 77163.4615 | 5.4231 | 6 | 6.1731 | More workers can speed up the construction process but might also require additional staging areas, impacting traffic.
15 | Temporary ancillary construction and re-work | 70.2 | 76.05 | 83.85 | 22 | 0.5 | 1442307.6923 | 1500000 | 1576923.0769 | 7.6923 | 8 | 8.4103 | Any re-work or temporary construction can significantly disrupt traffic flow and increase congestion.
16 | Extra excavation capacity | 60.45 | 76.05 | 81.9 | 23 | 0.5 | 134615.3846 | 150000 | 155769.2308 | 7.1795 | 8 | 8.3077 | Increased excavation work can significantly disrupt traffic, especially if additional lanes or areas need to be closed.
17 | Extra asphalt equipment and personnel | 101.4 | 101.4 | 107.25 | 26 | 0.5 | 200000 | 200000 | 205769.2308 | 8 | 8 | 8.2308 | This can accelerate road surfacing work but requires significant space and can lead to lane closures, heavily impacting traffic.
18 | Extra removal works | 42.9 | 50.7 | 52.65 | 28 | 0.5 | 69230.7692 | 75000 | 76442.3077 | 9.2308 | 10 | 10 | Removal of debris or existing structures can lead to significant traffic disruptions due to the need for lane closures and detours.
19 | Extra equipment and personnel | 9.75 | 13.65 | 15.6 | 30 | 0.5 | 214285.7143 | 250000 | 267857.1429 | 6.8571 | 8 | 8.5714 | Generally, more equipment and personnel can speed up work but might also require more space and lead to increased traffic disruption.
20 | Applying extra preloading material during the night | 40.95 | 50.7 | 50.7 | 9 | 0.5 | 1084615.3846 | 1200000 | 1200000 | 0.90385 | 1 | 1
21 | Automation of M&E workflows | 30 | 30 | 30 | 12 | 0.5 | 120000 | 120000 | 120000 | 0 | 0 | 0
22 | Welding operation during the night | 45 | 53 | 53 | 14 | 0.5 | 166415.0943 | 180000 | 180000 | 1.8491 | 2 | 2
23 | Extra temporary soil measures during the night | 32 | 40 | 42 | 15 | 0.5 | 315000 | 350000 | 358750 | 0.9 | 1 | 1.025
24 | Night shifts for concrete work | 67 | 80 | 91 | 21 | 0.5 | 91875 | 100000 | 106875 | 3.675 | 4 | 4.275
25 | Excavation during the night | 40 | 56 | 62 | 23 | 0.5 | 257142.8571 | 300000 | 316071.4286 | 0.85714 | 1 | 1.0536
26 | Removal works during the night | 33 | 41 | 43 | 28 | 0.5 | 81219.5122 | 90000 | 92195.122 | 0.90244 | 1 | 1.0244
27 | Lane by lane asphalt work | 30 | 30 | 30 | 26 | 0.5 | 430000 | 430000 | 430000 | 3 | 3 | 3
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum (pessimistic) capacity of the mitigation measure. The user must define this quantity.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely capacity of the mitigation measure. The user must define this quantity.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum (optimistic) capacity of the mitigation measure. The user must define this quantity.
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This factor defines to what extent the mitigation cost variation depends on the mitigation capacity variation. This factor is between 0 and 1. If this factor is set to 1, then the mitigation cost increases/decreases proportionally to the increase/decrease in he mitigation capacity. If it is set to 0, then the cost will remain constant regardless of the variation in the mitigation capacity. You may set any number between 0 and 1 (i.e., 0.5 means partial relation between the cost variation and the mitigation variation)
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Minimum cost of the mitigation measure. This is not a user input. It is automatically computed following a predefined formula. To add more cost items to the list, you may copy the formula from any of the cells below.
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Most-likely cost of the mitigation measure. This is a user input.
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Maximum cost of the mitigation measure. This is not a user input. It is automatically computed following a predefined formula. To add more cost items to the list, you may copy the formula from any of the cells below.

## Risks
Risk event ID | Risk event description | Minimum | Most likely | Maximum | Affected activities | Risk probability
1 | Preliminary design rejection, including extra scope of works | 96 | 105 | 119 | 3 | 0.2
2 | EDP audit failure | 13 | 14 | 15 | 4 | 0.05
3 | Existing condition Hollandse Brug deviates from maintenance plan made during tender phase | 63 | 70 | 78 | 7 | 0.15
4 | Unexpected gas conducts | 35 | 35 | 41 | 8 | 0.2
5 | Lower consolidation rate than calculated for | 34 | 35 | 40 | 9 | 0.1
6 | Piling machines break down | 14 | 14 | 15 | 10 | 0.1
7 | Late delivery of prefab elements | 19 | 21 | 25 | 11 | 0.2
8 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 22 | 12 | 0.25
9 | Production equipment failure | 20 | 21 | 23 | 14 | 0.05
10 | Construction site subsides | 13 | 14 | 15 | 15 | 0.05
11 | Ancillary equipment failure | 33 | 35 | 41 | 16 | 0.1
12 | Dynamic Traffic Management equipment / software not functioning | 20 | 21 | 21 | 18 | 0.25
13 | Discovery of polluted soil | 13 | 14 | 14 | 20 | 0.05
14 | Concrete casting failure | 13 | 14 | 14 | 21 | 0.05
15 | Main pillar subsides | 65 | 70 | 71 | 22 | 0.02
16 | Discovery of polluted soil | 25 | 28 | 32 | 23 | 0.05
17 | Insufficient quality of base layer | 39 | 42 | 47 | 26 | 0.02
18 | Discovery of asphalt with too high PAK percentage | 13 | 14 | 17 | 28 | 0.05
19 | Additional scope of work (misc.) | 130 | 140 | 160 | 30 | 0.01
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the minimum (optimistic) delay induced by the risk event. The user must define this quantity.
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the most-likely delay induced by the risk event. The user must define this quantity.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the maximum (pessimistic) delay induced by the risk event. The user must define this quantity.

## Correlation
Shared uncertainty factor (SUF)
SUF ID | SUF description | Minimum | Most likely | Maximum | Relations
1 |  | -45 | 0 | 72 | 10,11
2 |  | -50 | 0 | 100 | 21, 22, 23, 7
3 |  | -10 | 0 | 50 | 12, 23
4 |  | -45 | 0 | 110 | 20, 26
5 |  | -20 | 0 | 100 | 15, 16
6 |  | -5 | 0 | 100 | 16, 20
7 |  | -1 | 0 | 55 | 7, 20
8 |  | -20 | 0 | 50 | 8, 9
9 |  | -5 | 0 | 15 | 32, 33
10 |  | 0 | 0 | 45 | 18, 20
11 |  | -20 | 0 | 50 | 3, 4
12 |  | -20 | 0 | 100 | 7, 14
13 |  | -80 | 0 | 90 | 7, 16
14 | Weather | -140 | 0 | 100 | 7, 23
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID's of the shared uncertainty factors. Keep the ID's in order starting from 1
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Description of the shared uncertainity factors. It is not an essential input. Uncertainty factors can have an impact on the duration of construction activities. These factors may simultaneously influence multiple activities Note that the correlation section is only necessary for the advanced version of the MitC (not the basic)
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The ID's of correlated activities that share the uncertainty factor. This is a user input. You may insert more than one activity by separating them with a space or a comma.